## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Resource Allocation | Estimated Effort (hrs) | Dependencies | Progress (%)
T-001 | Market Research Phase | Sarah Johnson | 2024-03-15 | High | In Progress | Marketing Team, Analysts | 80 | None | 65%
T-002 | Product Design Finalization | Mike Chen | 2024-04-10 | High | Not Started | Design Team, UX Experts | 120 | T-001 | 0%
T-003 | Development Sprint 1 | Lisa Rodriguez | 2024-05-05 | Medium | Planned | Engineering Team, QA | 160 | T-002 | 15%
T-004 | User Testing & Feedback Loop | David Kim | 2024-06-15 | Medium | Scheduled | QA Team, Product Managers | 90 | T-003 | 5%
T-005 | Deployment & Go-Live | Emma Watson | 2024-07-10 | High | Not Started | Operations, DevOps | 100 | T-004 | 0%