## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Resources Required | Estimated Hours | Progress (%)
TP-001 | Develop Project Timeline | Sarah Johnson | High | 2024-03-15 | In Progress | Project Manager, Analysts | 20 | 65%
TP-002 | Finalize Budget Allocation | Michael Lee | Medium | 2024-03-20 | Pending | Finance Team, CFO | 15 | 0%
TP-003 | Conduct Stakeholder Workshop | Lisa Chen | High | 2024-03-18 | Planned | Facilitator, Marketing Lead | 8 | 0%
TP-004 | Review Risk Mitigation Plan | David Kim | Medium | 2024-03-25 | Not Started | Risk Officer, Legal Advisor | 10 | 0%