## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Resource Required | Estimated Hours | Dependencies
T-001 | Project Kickoff Meeting | J. Smith | 2023-10-15 | High | Planned | Project Manager, Team Lead | 2
T-002 | Requirement Gathering | A. Johnson | 2023-11-05 | High | In Progress | Business Analyst, Stakeholders | 8.5 | T-001
T-003 | UI/UX Design Finalization | M. Lee | 2023-11-20 | Medium | Not Started | UI Designer, UX Researcher | 6 | T-002
T-004 | Development Phase Start | R. Patel | 2023-12-01 | High | Not Started | Software Developers, QA Lead | 40 | T-003
T-005 | System Testing & Validation | S. Williams | 2024-01-15 | High | Not Started | QA Team, DevOps | 20 | T-004