## Worksheet
Task ID | Task Name | Owner | Department | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%) | Dependencies | Notes
TASK-001 | System Migration Planning | John Smith | IT Infrastructure | 2024-03-15 | 2024-04-10 | In Progress | High | 80 | 65 | 75% | TASK-002, TASK-003 | Coordinate with cloud provider for data transfer strategy.
TASK-002 | User Training Schedule | Maria Lopez | HR & Operations | 2024-03-20 | 2024-04-15 | Not Started | Medium | 40 | 0 | 0% | TASK-001 | Prepare training modules and schedule sessions for department heads.
TASK-003 | Security Audit Preparation | David Chen | Cybersecurity | 2024-03-18 | 2024-04-05 | On Hold | High | 60 | 25 | 42% | TASK-001, TASK-004 | Awaiting approval from compliance board.
TASK-004 | Budget Reallocation Review | Sarah Kim | Finance | 2024-03-25 | 2024-04-18 | Not Started | Medium | 50 | 0 | 0% |  | Evaluate current spending vs. projected resource needs.