## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Resources Required | Estimated Effort (hrs) | Dependencies | Notes
T001 | Conduct Market Research | John Smith | 2024-03-15 | High | In Progress | Marketing Team, Analysts | 40 | None
T002 | Develop Product Roadmap | Sarah Lee | 2024-04-01 | Medium | Not Started | Product Managers, UX Designers | 60 | T001 Completed
T003 | Implement User Feedback System | Mike Chen | 2024-05-10 | High | Planned | Engineering, Support Team | 80 | T002 Completed | Ensure integration with CRM.
T004 | Train Customer Support Staff | Lisa Wong | 2024-04-25 | Medium | Not Started | Support Team, Training Lead | 20 | T003 Completed | Include live demo session.
T005 | Conduct Q1 Performance Review | Alex Turner | 2024-06-15 | Low | Not Started | Management Team, Finance | 30 | T004 Completed