## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Resources Required | Dependencies | Progress (%) | Notes
TP-001 | Initial Resource Assessment | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | High | HR, Finance, IT | -- | 65% | Review staffing needs across departments.
TP-002 | Procure Equipment | Mike Johnson | 2024-04-16 | 2024-05-31 | Pending Approval | Medium | Procurement Team, Logistics | -- | 0% | Awaiting budget sign-off from CFO.
TP-003 | Train Staff on New Tools | Sarah Lee | 2024-05-01 | 2024-05-20 | Completed | Medium | Training Department, HR | TP-001 | 100% | All team members completed certification.
TP-004 | Develop Resource Allocation Model | David Brown | 2024-06-01 | Planned | High | Data Analytics, Operations | TP-002, TP-003 | 0% | Model will optimize staff distribution.