## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Resource Allocation | Dependencies | Progress (%)
TASK-001 | Finalize Q4 Budget Proposal | John Doe | 2023-12-15 | High | In Progress | Finance Team, 3 FTEs | Task ID: TASK-002, TASK-003 | 75%
TASK-002 | Conduct Market Research Survey | Sarah Lee | 2023-11-30 | Medium | Not Started | Marketing Team, 2 FTEs | Task ID: TASK-004 | 0%
TASK-003 | Develop Product Roadmap | Michael Chen | 2023-12-05 | High | Scheduled | Product Team, 4 FTEs | Task ID: TASK-001 | 20%
TASK-004 | Design UI/UX for Mobile App | Lisa Wong | 2023-12-10 | High | Not Started | Design Team, 3 FTEs | Task ID: TASK-002 | 0%
TASK-005 | Launch Training Program | <David Kim | 2024-01-15 | Medium | Planned | HR & Learning Team, 2 FTEs | Task ID: TASK-006 | 10%