## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Resource Required | Dependencies | Progress (%)
T001 | Project Initiation Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | Medium | Project Manager, Finance Lead |  | 100%
T002 | Market Research SurveySarah Johnson | 2024-03-18 | 2024-04-05 | In Progress | High | Research Team, Data Analysts | T001 | 65%
T003 | Develop Product Prototype | Michael Lee | 2024-04-10 | 2024-05-15 | Not Started | Medium | UX Designers, Engineers | T002 | 0%
T004 | Vendor Onboarding | Linda Wong | 2024-04-25 | 2024-05-10 | Completed | Low | Procurement Team, Legal | T001 | 100%
T005 | Final Review & Sign-off | John Smith | 2024-05-20 | 2024-05-25 | In Progress | High | Project Manager, QA Team | T003, T004 | 30%