## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Resources Required | Dependencies | Notes
TASK-001 | Market Research Phase | John Smith | 2024-03-01 | 2024-03-15 | In Progress | High | Research Team, Analysts | None | Gather customer feedback and competitor data.
TASK-002 | Product Design Finalization | Lisa Chen | 2024-03-16 | 2024-04-05 | Planned | High | Design Team, UX Specialists | TASK-001 | Finalize wireframes and prototypes.
TASK-003 | Development Sprint Planning | Mike Brown | 2024-04-06 | 2024-05-31 | Not Started | Medium | Engineering Team, QA Lead | TASK-002 | Plan sprints and assign features.
TASK-004 | User Testing & Feedback | Sarah Davis | 2024-06-01 | 2024-06-30 | Scheduled | High | Beta Testers, Product Manager | TASK-003 | Collect real user experience data.
TASK-005 | Go-Live Deployment | Team Lead | 2024-07-01 | 2024-07-05 | Not Started | Critical | DevOps, Support Team | TASK-004 | Deploy to production environment.