## Worksheet
Task ID | Task Name | Owner | Priority | Due Date | Status | Resource Allocation | Estimated Hours | Progress (%)
TASK-001 | Project Kickoff Meeting | Jane Smith | High | 2023-10-05 | In Progress | Project Manager, Team Lead | 4 | 65%
TASK-002 | Requirement Gathering Workshop | Mark Johnson | Medium | 2023-10-12 | Not Started | Business Analyst, UX Designer | 8 | 0%
TASK-003 | Technical Design Review | Sarah Lee | High | 2023-10-20 | Scheduled | Lead Developer, QA Engineer | 12 | 30%
TASK-004 | Development Phase - MVP | Team A | High | 2023-11-05 | Not Started | Full Development Team | 40 | 0%
TASK-005 | User Acceptance Testing | David Brown | Medium | 2023-11-25 | Planned | QA Team, UX Team | 16 | 0%