## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Estimated Hours | Resource Group
T-001 | Define Resource Planning Strategy | John Doe | 2024-04-15 | High | In Progress | 8 | Strategic Planning
T-002 | <Allocate Budget for Q2 Operations | Sarah Lee | 2024-05-10 | Medium | Pending | 12 | Finance & Budgeting
T-003 | Conduct Team Skill Assessment | Mike Chen | 2024-04-28 | High | Not Started | 6 | Human Resources
T-004 | Review Vendor Contracts | Lisa Wong | 2024-05-05 | Medium | In Progress | 10 | Procurement
T-005 | Implement Resource Allocation Dashboard | David Kim | 2024-06-15 | High | Not Started | 20 | IT & Operations