## Worksheet
Task ID | Task Name | Owner | Assigned Date | Due Date | Priority | Status | Resource Required | Progress % | Notes
T-001 | Project Kickoff Meeting | Sarah Chen | 2024-04-01 | 2024-04-05 | High | In Progress | Project Manager, 1 Designer | 75% | Confirm team availability and deliverables.
T-002 | Market Research Phase | David Kim | 2024-04-03 | 2024-04-15 | Medium | Not Started | Researcher, 3 Analysts | 0% | Gather data from primary and secondary sources.
T-003 | UI/UX Design Finalization | Lisa Patel | 2024-04-10 | 2024-05-10 | High | In Progress | Designer, 2 Developers | 50% | Final prototypes to be reviewed by stakeholders.
T-004 | Development Sprint 1 | James Wilson | 2024-04-15 | 2024-05-15 | High | Not Started | Backend Team, 4 Engineers | 0% | Implement core features based on design.
T-005 | QA Testing & Bug Resolution | Rachel Torres | 2024-05-10 | 2024-05-31 | Medium | Planned | QA Team, 3 Testers | 0% | Conduct end-to-end testing and fix critical bugs.