## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Progress (%) | Dependencies | Notes
T001 | Finalize Q4 Budget Proposal | Sarah Johnson | 2023-10-01 | 2023-10-15 | In Progress | High | 65% | T002, T003 | Review with Finance Team by Oct 10.
T002 | Update Project Scope Document | David Chen | 2023-10-05 | 2023-10-12 | Not Started | Medium | 0% |  | Draft to be approved by PM.
T003 | Conduct Stakeholder Workshop | Lisa Rodriguez | 2023-10-10 | 2023-10-14 | On Hold | High | 30% | T001 | Pending final budget confirmation.
T004 | Develop Risk Mitigation Plan | James Wilson | 2023-10-18 | 2023-11-05 | Not Started | High | 0% |  | Align with Legal and Compliance.