## Worksheet
Date | Task | Resource Assigned | Duration (Hours) | Start Time | End Time | Status | Notes
2024-04-01 | Develop project timeline | John Doe (Project Manager) | 8 | 09:00 | 17:00 | Completed | Preliminary draft approved by team lead.
2024-04-02 | Team meeting – sprint planning | Project Team (5 members) | 4.5 | 10:30 | 15:30 | Completed | All tasks aligned; milestones set.
2024-04-03 | Design user interface mockups | Sarah Lee (UI/UX Designer) | 6 | 14:00 | 20:00 | In Progress | Feedback requested from stakeholders.
2024-04-05 | Code review – frontend module | Mike Chen (Developer) | 3.5 | 11:00 | 14:30 | Completed | No critical issues found.
2024-04-06 | Resource allocation review | HR & Project Management Office | 2 | 13:00 | 15:00 | Completed | Updated resource availability chart.
Total Hours Logged |  |  |  | 24