## Worksheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Resource Required | Dependencies | Estimated Effort (hrs) | Progress %
RP-001 | Finalize Q4 budget allocation | Sarah Johnson | High | 2023-10-30 | In Progress | Finance Team, HR Dept | Q3 Financial Review | 40 | 65%
RP-002 | Onboard new IT infrastructure | Michael Chen | Critical | 2023-11-05 | Not Started | IT Operations, Cybersecurity Team | None | 80 | 0%
RP-003 | Conduct staff capacity assessment | Lisa Rodriguez | Medium | 2023-10-25 | Completed | HR, Training Dept | Q4 Planning Meeting | 30 | 100%
RP-004 | Update resource utilization dashboard | David Kim | High | 2023-10-31 | In Progress | Data Analytics Team | Q3 Report Finalization | 50 | 40%
RP-005 | Plan vendor contract renewal process | Emma Thompson | Medium | 2023-11-08 | Not Started | Procurement, Legal Dept | Vendor Evaluation Report | 35 | 0%