## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Conduct resource availability assessment | Alex Morgan | 2024-04-15 | In Progress | High | Review staffing levels across departments.
Finalize team skill matrix | Sara Chen | 2024-04-20 | Completed | Medium | Share with HR for validation.
Identify gap in project resources | Jordan Lee | 2024-04-25 | Pending | High | Compare current vs. required skill sets.
Plan resource reallocation for Q2 | Team Lead | 2024-05-01 | Not Started | Critical | Align with department heads and budget.
Review capacity utilization reports | Nina Patel | 2024-04-30 | In Progress | Medium | Analyze performance trends.