## Worksheet
Week | Resource | Assigned Task | Start Date | End Date | Status | Capacity Utilization (%) | Dependency Notes
Week 1 | Team Lead A | Project Initiation Review | 2023-10-09 | 2023-10-13 | Pending Approval | 75% | Requires stakeholder sign-off
Week 1 | Developer B | Backend API Design | 2023-10-10 | 2023-10-14 | In Progress | 85% | Depends on frontend wireframes
Week 2 | QA Engineer C | Unit Testing Phase | 2023-10-16 | 2023-10-20 | Scheduled | 60% | Aligned with dev sprint milestone
Week 2 | UX Designer D | User Journey Mapping | 2023-10-17 | 2023-10-21 | On Hold | 45% | Pending client feedback on current drafts
Week 3 | Project Manager E | Weekly Resource Alignment Meeting | 2023-10-24 | 2023-10-28 | Completed | 90% | All teams updated on priorities