## Worksheet
Week of | Project Name | Resource Assigned | Hours Allocated | Status | Notes/Comments
April 7 - April 13, 2024 | Client Onboarding Phase | Jane Smith (PM) | 16 | On Track | Meeting scheduled with stakeholders to finalize scope.
April 14 - April 20, 2024 | UI/UX Design Development | Michael Chen (Designer) | 20 | In Progress | Final wireframes approved by client. Next review in 3 days.
April 21 - April 27, 2024 | Development Sprint | Lisa Rodriguez (Dev) | 32 | Scheduled | Frontend and backend integration in progress.
April 28 - May 4, 2024 | QA & Testing Phase | David Kim (QA) | 18 | Pending Start | Test environments ready. Client to confirm access.
May 5 - May 11, 2024 | Client Review & Final Sign-Off | All Team Members | 24 | Planned | Final presentation scheduled for May 8.