## Worksheet
Week | Resource | Assigned Task | Start Date | End Date | Status | Capacity Utilization (%) | Notes
Week 1 | Engineer A | System Integration Review | 2024-04-01 | 2024-04-05 | Completed | 85% | Initial design validated.
Week 2 | Developer B | API Development Phase | 2024-04-08 | 2024-04-15 | In Progress | 65% | Testing environment ready.
Week 3 | Analyst C | Resource Demand Forecasting | 2024-04-16 | 2024-04-22 | Planned | 70% | Baseline data collected.
Week 4 | Project Manager D | Weekly Resource Alignment Meeting | 2024-04-23 | 2024-04-27 | Completed | 100% | All team members present.
Week 5 | QA Lead E | End-to-End Testing Phase | 2024-04-30 | 2024-05-06 | Pending Approval | 45% | Waiting for stakeholder sign-off.