## Worksheet
Risk Category | Risk Description | Likelihood (1-5) | Impact (1-5) th> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Employee | Action Plan (Q1-Q4) | Budget Allocation (USD) | Status
Cybersecurity | Unauthorized access to sensitive employee data due to outdated systems. | 4 | 5 | 20 | Implement multi-factor authentication and system patching. | Jane Smith | Q1 - Patch systems; Q2 - Train staff; Q3 - Conduct audit; Q4 - Review controls. | 15,000 | Active
Data Privacy | Potential breach of customer personal information during data transfer. | 3 | 4 | <">12
Compliance Risk | Failure to meet regulatory requirements due to documentation gaps. | 2 | 3 | 6 | Conduct quarterly compliance reviews and update policy documentation. | Mark Johnson | Q1 - Audit current policies; Q2 - Update records; Q3 - Train team; Q4 - Review findings. | 8,000 | Planned
Operational Disruption | Server downtime due to hardware failure. | 4 | 4 | 16 | Deploy redundant servers and automated failover systems. | Lisa Wong | Q1 - Install backup infrastructure; Q2 - Test failover; Q3 - Monitor performance; Q4 - Evaluate improvements. | 20,000 | In Progress