## Worksheet
Risk Item | Risk Category | Likelihood | Impact | Risk Score (L × I) | Mitigation Strategy | Responsible Party | Target Completion Date | Current Status | Last Updated
Data Breach | Cybersecurity | High | Critical | 9 | Implement multi-factor authentication and regular penetration testing | IT Security Team | 2024-06-30 | In Progress | 2024-04-15
Supply Chain Disruption | Operational Risk | Medium | High | 6 | Diversify suppliers and establish backup logistics | Procurement Office | 2024-07-15 | Planned | 2024-04-10
Regulatory Non-Compliance | Legal & Compliance | Low | Critical | 3 | Conduct annual compliance audits and training programs | Compliance Officer | 2024-09-30 | On Track | 2024-04-05
System Downtime | IT Infrastructure | High | Medium | 6 | Upgrade failover systems and implement monitoring tools | IT Operations Team | 2024-08-20 | In Progress | 2024-04-18