## Worksheet
Risk Item | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Responsible Party | Timeline | Budget Allocation (USD) | Status
Supply Chain Disruption | Delays in raw material delivery due to geopolitical or logistical issues. | 4 | 5 | 20 | Diversify suppliers and maintain safety stock. | Procurement Manager | Q3–Q4 | $50,000 | Active
Cybersecurity Breach | Unauthorized access to sensitive customer or financial data. | 5 | 5 | 25 | Implement multi-factor authentication and regular penetration testing. | CISO | Ongoing | $100,000 | In Progress
Regulatory Non-Compliance | Failure to meet evolving industry regulations. | 3 | 4 | 12 | Conduct compliance audits and training programs. | Compliance Officer | Annual | $30,000 | Completed
Market Demand Fluctuation | Sudden decrease in customer demand leading to overstock. | 2 | 4 | 8 | Adopt dynamic pricing and inventory forecasting tools. | Operations Manager | Q4 | $40,000 | Planned