## Worksheet
Item | Description | Risk Category | Likelihood | Impact | Priority | Mitigation Strategy | Responsible Party | Due Date
1 | Project scope change without formal approval | Scope Risk | Moderate (3/5) | Impact | P2 - High Priority | Implement formal change control process | Project Manager | 2024-04-15
1.1 | Late delivery due to third-party vendor delays | Supply Chain Risk | High (4/5) | Severe (5/5)
|  |  |  | P1 - Critical Priority | Vendor Management Team | 2024-04-30
1.2 | Data breach due to unpatched systems | Security Risk | High (4/5) | High (4/5) | P1 - Critical Priority | Conduct system patching and access review | CIO & IT Security Team | 2024-03-31
1.3 | Team turnover leading to knowledge gaps | Human Resource Risk | Moderate (3/5) | Moderate (3/5) | P3 - Low Priority | Establish knowledge transfer protocol | HR & Project Manager | 2024-05-10