## Worksheet
Risk Identification | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Priority | Mitigation Strategy | Responsible Party | Timeline | Budget Allocation ($)
Operational Failure | Critical system downtime due to hardware failure. | 4 | 5 | High (20) | Implement redundant servers and automated failover. | IT Manager | Q1 2024 - Q4 2024 | $50,000
Data Breach | Unauthorized access to sensitive customer data. | 3 | 5 | <High (15) | Enhance firewall, multi-factor authentication, and encryption. | CISO | Ongoing | $75,000
Market Volatility | Unpredictable changes in market conditions affecting revenue. | 2 | 4 | Medium (8) | Diversify product portfolio and maintain flexible pricing. | Finance Director | Q2 2024 - Q4 2024 | $30,000
Supply Chain Disruption | Delay in delivery from key suppliers due to logistics issues. | 3 | 4 | Medium (12) | Identify alternative suppliers and build buffer inventory. | Procurement Lead | Q1 2024 - Q3 2024 | $25,000
Regulatory Change | New compliance requirements affecting business operations. | 2 | 5 | High (10) | Establish regulatory monitoring team and conduct audits. | Legal Officer | Ongoing | $40,000