## Worksheet
Date | Risk Identifier | Risk Description | Likelihood | Impact th> | Risk Rating | Mitigation Strategy | Responsible Person | Monitoring Frequency
2023-10-01 | RISK-001 | System outage due to server failure | High | Critical | High | Implement redundant servers and backup protocols | John Smith | Daily
2023-10-01 | RISK-002 | Data breach from unsecured endpoints | Medium | High | High | Enforce endpoint encryption and access controls | Lisa Chen | Daily
2023-10-01 | RISK-003 | Supply chain delay affecting delivery timelines | Low | Medium | Medium | Diversify suppliers and maintain safety stock | Mark Davis | Weekly
2023-10-02 | RISK-004 | Regulatory compliance failure due to manual reporting errors | Medium | High | High | Automate compliance reporting with audit trail logs | Sarah Lee | Daily