## Worksheet
Risk Item | Category | Likelihood (1–5) | Impact (1–5) | Risk Score | Mitigation Strategy | Responsible Party | Timeline | Status
Data Breach | Security | 4 | 5 | 20 | Implement multi-factor authentication and regular audits | IT Security Team | Q3 2024 | In Progress
Supply Chain Disruption | Operations | 3 | 4 | 12 | Diversify suppliers and establish backup sources | Procurement Manager | Q4 2024 | Planned
Regulatory Non-Compliance | Legal | 2 | 5 | 10 | Conduct compliance training and update policies | Compliance Officer | Ongoing | Active
Technology Failure | IT Infrastructure | 5 | 4 | 20 | Redundant systems and failover protocols | IT Operations | Immediate Action | Critical