## Worksheet
Risk Identification | Risk Description | Impact Level (Low/Medium/High/Critical) | Likelihood (Low/Medium/High/Critical) | Risk Score (Impact × Likelihood) | Mitigation Strategy | Responsible Party | Timeline | Monitoring Frequency | Status (Open/Resolved/Closed)
RISK-001 | Loss of critical server due to hardware failure | High | Medium | High | Implement redundant servers and automatic failover protocols | IT Operations Team | Q1 2024 – Q4 2024 | Quarterly review | Open
RISK-002 | Security breach due to outdated software | Critical | High | Critical | Apply regular patch management and conduct vulnerability scans monthly | Security & Compliance Officer | Immediate – Ongoing | Bimonthly audit | Open
RISK-003 | Regulatory non-compliance due to poor documentation | Medium | Medium | Medium | Introduce standardized compliance templates and review processes | Legal & Compliance Department | Q2 2024 – Q3 2024 | Semesterly review | Open
RISK-004 | Supply chain delay affecting project delivery | High | Medium | High | Establish dual sourcing and maintain safety stock for key components | Procurement Manager | Q1 2024 – Q4 2024 | Semesterly review | Open
RISK-005 | Data privacy violation due to employee error | High | Low | Medium | Conduct mandatory data handling training and implement access controls | HR & IT Administration | Ongoing (annual refresh) | Annual training and audit | Open