## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsible Employee | Due Date | Status
Data Breach | Unauthorized access to sensitive employee and customer data. | High | High | Critical | Implement multi-factor authentication and regular audits. | Alex Johnson | 2024-06-15 | In Progress
System Downtime | Critical business systems fail during peak hours. | Medium | High | High | Redundant servers and automated failover protocols. | Sam Rivera | 2024-06-20 | Not Started
Compliance Failure | Failure to meet regulatory requirements (e.g., GDPR, HIPAA). | Low | High | Medium | Quarterly compliance review and training updates. | Maya Patel | 2024-05-30 | Completed
Third-Party Vendor Risk | Vendor security practices are insufficient. | Medium | Medium | Moderate | Conduct annual vendor risk assessments. | Jordan Lee | 2024-07-10 | Planned