## Worksheet
Risk ID | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Timeline | Budget Allocation ($) | Status
RISK-001 | Supply chain disruption due to geopolitical tensions | High | High | 9 | Diversify suppliers; establish backup logistics | Procurement Team | Q3 2024 – Q4 2025 | $150,000 | Active
RISK-002 | Data breach due to outdated software | Medium | High | 6 | Software update and penetration testing | IT Security Team | Q2 2024 – Q1 2025 | $80,000 | In Progress
RISK-003 | Key employee turnover in R&D department | Low | Medium | 3 | Employee retention program and succession planning | HR Department | Ongoing | $30,000 | Planned
RISK-004 | Regulatory changes affecting compliance | High | Medium | 6 | Monitor regulatory updates and conduct audits | Legal & Compliance Team | Q1 2025 – Ongoing | $50,000 | Active