## Worksheet
Risk Identification | Risk Description | Likelihood | Impact th> | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Timeline | Status
R-001 | Project scope creep due to stakeholder demands | High | Medium | 6 | Implement change control board and formal approval process | Project Manager | Q1 2024 | Active
R-002 | Delays in third-party vendor delivery | Medium | High | 6 | Establish backup vendors and buffer time in schedule | Procurement Lead | Ongoing | Monitoring
R-003 | Technical failure of key software platform | High | Critical | 12 | Deploy redundant systems and conduct regular stress testing | IT Director | Immediate to Q2 2024 | Pending Review
R-004 | Key team member resignation | Low | High | 3 | Implement cross-training and succession planning | HR & Team Lead | Q4 2024 | Planned