## Worksheet
Risk Identification | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Timeline | Status
Operational Failure | Critical system downtime due to software bugs. | 4 | 5 | 20 | Implement automated testing and rollback procedures. | IT Department | Q3 2024 | Active
Data Breach | Unauthorized access to sensitive customer data. | 3 | 5 | 15 | Enhance firewall protocols and conduct regular audits. | Security Team | Ongoing | Monitoring
Market Volatility | Sudden shifts in market conditions affecting revenue. | 4 | 4 | 16 | Diversify supply chain and maintain flexible pricing. | Finance & Strategy | Q4 2024 | Planned
Regulatory Change | New compliance laws requiring changes in operations. | 2 | 4 | 8 | Establish compliance task force and review policy updates. | Legal Department | Q2 2025 | Pending
Supply Chain Disruption | Major supplier failure or transportation issues. | 5 | 3 | 15 | Identify alternate suppliers and build inventory buffers. | Procurement Team | Immediate Action | Active