## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Timeline | Status
Technical Failure | Critical system components may fail due to aging or environmental stress. | High | High | 9 | Implement redundant systems and regular preventive maintenance. | IT Operations Team | Q1 2024 – Q4 2024 | Planned
Data Breach | Unauthorized access to sensitive customer data. | Medium | Very High | 6 | Strengthen encryption, conduct regular audits, and employee training. | Security & Compliance Office | Ongoing | Active
Regulatory Change | New compliance requirements may affect operations. | Low | High | 3 | Monitor regulatory updates and engage legal advisors early. | Legal Department | Q2 2024 onwards | Under Review
Supply Chain Disruption | Key vendors may face operational or geopolitical issues. | Medium | Medium | 4 | Diversify suppliers and maintain safety stock. | Procurement Team | Q1 2024 – Q3 2024 | In Progress
Human Error | Mistakes made by staff during system operation or data entry. | High | Medium | 6 | Implement double-check procedures and training programs. | All Departments | Ongoing | Planned