## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Due Date
Project Delay | Unplanned delays due to scope changes or resource shortages. | Medium | High | 6 | Implement agile milestones and weekly reviews. | Project Manager | 2024-03-15
Budget Overrun | Exceeding allocated budget due to cost inflation or scope creep. | High | <Medium | 6 | Establish cost control checkpoints and approval thresholds. | Finance Officer | 2024-03-20
Technology Failure | System downtime or data loss due to technical issues. | Low | Critical | 3 | Deploy redundant systems and backup protocols. | IT Director | 2024-03-10
Regulatory Change | New compliance rules affecting project deliverables. | Medium | High | 6 | Conduct regular regulatory audits and update policies. | Legal Counsel | 2024-03-30