## Worksheet
Risk Item | Risk Description | Probability | Impact | Likelihood x Impact (Score) | Risk Priority | Mitigation Strategy | Responsible Team Member | Deadline | Status
Project Delay | Delays in project milestones due to external dependencies. | Medium | High | 6 | High Priority | Establish clear milestone tracking and contingency planning. | Project Manager | 2024-06-30 | In Progress
Budget Overrun | Exceeding approved budget due to unplanned expenses. | Low | High | 3 | Medium Priority | Implement cost tracking and monthly budget reviews. | Finance Lead | 2024-07-15 | Planned
Technical Failure | System crash or software bug impacting user access. | High | Medium | 6 | High Priority | Conduct regular system audits and implement rollback plans. | IT Team | 2024-08-10 | Pending Review
Regulatory Change | Unexpected changes in compliance laws affecting operations. | Medium | High | 5 | High Priority | Monitor regulatory updates and assign legal compliance team. | Legal Officer | 2024-09-01Not Started