## Worksheet
Date | Risk Identified | Risk Level (Low/Medium/High) | Impact Assessment | Likelihood | Mitigation Strategy | Owner | Resolution Status
2023-10-05 | Supply chain disruption due to logistics delay | High | Production delays, increased costs | Medium | Identify alternative suppliers and diversify logistics routes | Operations Manager | In Progress
2023-10-05 | Key employee turnover | Medium | Loss of expertise and knowledge transfer issues | High | Implement retention program and strengthen onboarding process | HR Director | Planned
2023-10-05 | IT system downtime | High | Business operations halted, data loss risk | Medium | Deploy redundant servers and backup systems | IT Lead | Completed