## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact(th) | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Review Date
Market Volatility | Fluctuations in market conditions may affect revenue projections. | Medium | High | High | Diversify product offerings and implement dynamic pricing models. | Marketing Director | 2024-06-30
Supply Chain Disruption | Delays or failures in supplier deliveries may impact production timelines. | High | Medium | High | Maintain backup suppliers and improve inventory forecasting. | Sourcing Manager | 2024-07-15
Data Security Breach | Unauthorized access to customer data could result in legal and reputational damage. | Low | Very High | Very High | Enhance encryption protocols and conduct regular security audits. | CIO | 2024-08-10
Regulatory Changes | New laws or regulations may require costly compliance adjustments. | Medium | High | High | Establish a regulatory monitoring team and update policy frameworks quarterly. | Legal Counsel | 2024-09-05