## Worksheet
Risk Category | Risk Description | Likelihood | Impact th> | Risk Rating | Mitigation Strategy | Owner | Review Date
Market Volatility | Fluctuations in consumer demand or market trends may affect revenue. | Medium | High | High | Diversify product portfolio and conduct regular market analysis. | Risk Manager | 2024-03-15
Technology Failure | <System outages or cybersecurity breaches could disrupt operations. | High | <Medium | High | Implement redundancy and regular security audits. | CIO | 2024-04-10
Regulatory Change | New or updated regulations may require costly compliance changes. | Low | High | Medium | Establish a regulatory monitoring team and conduct scenario planning. | Legal Officer | 2024-05-01
Talent Shortage | <Difficulty in recruiting skilled personnel may delay project timelines. | Medium | Medium | Medium | Expand recruitment channels and invest in internal development programs. | HR Director | 2024-06-15
Supply Chain Disruption | Delays or interruptions in supplier deliveries could impact production. | High | Medium | High | Maintain backup suppliers and develop alternative logistics plans. | Sourcing Manager | 2024-07-10