## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Rating (Likelihood × Impact) | Mitigation Strategy | Responsibility | Review Date | Status
Market Volatility | Fluctuations in market conditions affecting revenue projections. | Medium | High | 6 | Diversify product portfolio and implement dynamic pricing models. | Risk Management Team | 2024-04-15 | Active
Supply Chain Disruption | Delays or interruptions in supplier deliveries. | High | Medium | 6 | Maintain safety stock and identify alternative suppliers. | Purchasing Department | 2024-05-10 | In Review
Data Breach | Unauthorized access or disclosure of sensitive customer data. | Low | Very High | 4 | Enhance cybersecurity protocols and conduct regular audits. | CISO Office | 2024-06-01Pending Approval
Regulatory Change | Unforeseen changes in compliance laws impacting operations. | Medium | High | 6 | Establish a compliance monitoring team and conduct quarterly reviews. | Legal Department | 2024-03-20 | Completed