## Worksheet
Risk Identification | Risk Description | Impact Level | Probability | Risk Rating (Impact x Probability) | Mitigation Strategy | Responsible Party | Timeline | Status
Market Volatility | Unpredictable fluctuations in market prices affecting revenue projections. | High | Medium | High | Diversify investment portfolio and implement hedging instruments. | Finance Director | Q3 2024 - Ongoing | Active
Regulatory Change | New legislation may require significant compliance adjustments. | High | <Low | Medium | Establish a cross-functional compliance task force and conduct early reviews. | Legal & Compliance Officer | Q2 2024 - Q1 2025 | Planned
Supply Chain Disruption | Potential delays or failure in key supplier deliveries. | Medium | High | High | Identify alternative suppliers and build safety stock inventory. | Operations Manager | Ongoing | In Progress
Cybersecurity Breach | Unauthorized access or data theft leading to reputational harm. | Critical | Medium | High | Deploy advanced firewall, conduct regular audits, and train staff on security protocols. | CIO & IT Security Team | Immediate - Annual Reviews | Monitored