## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Current Status | Ownership | Mitigation Strategy | Response Plan | Last Reviewed
RISK-001 | Cybersecurity breach due to outdated software | Technology | High | High | Active | IT Security Team | Patch all systems quarterly; conduct penetration testing biannually. | Implement incident response protocol and notify stakeholders within 1 hour. | 2024-03-15
RISK-002 | Supply chain disruption from key vendor failure | Operations | Medium | High | Monitor | Procurement Department | Diversify vendor base; establish backup suppliers. | Develop alternate sourcing plans and conduct scenario analysis. | 2024-04-10
RISK-003 | Regulatory non-compliance in data handling | Compliance | High | Medium | Planned Review | Legal & Compliance Office | Conduct compliance audits; update policies annually. | Establish data governance team and training programs. | 2024-05-01
RISK-004 | Key personnel departure leading to knowledge gaps | Human Resources | Medium | High | Active | HR & Operations Leadership | Document critical knowledge; implement cross-training. | Develop succession plans and employee onboarding protocols. | 2024-03-20