## Worksheet
Risk Identification | Risk Description | Likelihood | Impact |  | Risk Rating | Mitigation Strategy | Owner | Review Date
Market Volatility | Fluctuations in market prices affecting revenue projections. | Medium | High | High | Diversify investment portfolio and implement hedging strategies. | Finance Director | 2024-06-30
Supply Chain Disruption | Delays or interruptions in raw material delivery. | High | Medium | <High | Establish backup suppliers and improve logistics planning. | Operations Manager | 2024-07-15
Cybersecurity Breach | Unauthorized access to sensitive customer data. | Medium | Critical | Critical | Deploy advanced firewalls, conduct regular audits, and train staff. | CISO | 2024-08-01
Regulatory Change | New legislation impacting compliance obligations. | Low | High | High | Establish a compliance monitoring team and track policy updates. | Legal Counsel | 2024-09-10