## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsibility | Timeline | Status
1 | System outage due to hardware failure | High | Critical | 9 | Implement redundant servers and regular maintenance checks | IT Department | Q1 2024 | Active
2 | Data breach from unsecured access points | Medium | High | 6 | Enforce multi-factor authentication and access controls | Security Team | Ongoing | In Progress
3 | Regulatory non-compliance due to policy gaps | Low | Critical | 3 | Conduct quarterly compliance audits and update policies | Legal & Compliance | Q4 2024 | Planned
4 | Supply chain delays affecting delivery timelines | High | Medium | 6 | Diversify suppliers and build buffer inventory | Procurement Team | Q3 2024 | Active