## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood (1–5) | Impact (1–5) | Risk Score | Owner | Current Controls | Mitigation Strategy | Action Plan | Due Date | Status | Review Date
RISK-001 | Failure of key supplier to deliver critical components on time. | Supply Chain | 4 | 5 | 20 | Procurement Manager | Dual sourcing, contract penalties | Establish alternative suppliers and negotiate SLAs. | Identify backup vendors by Q3; finalize contracts by Oct 30. | 2024-10-30 | In Progress | 2024-11-30
RISK-002 | Cybersecurity breach due to outdated software. | IT Security | 3 | 5 | 15 | IT Security Lead | Firewall updates, endpoint protection | Patch all systems and conduct penetration testing. | Complete patching by Nov 15; test by Nov 20. | 2024-11-15 | Planned | 2024-11-30
RISK-003 | Regulatory non-compliance due to data handling errors. | Compliance | 4 | 4 | 16 | Legal & Compliance Officer | Data encryption, access logs monitoring | Conduct staff training and update privacy policies. | Training scheduled for Dec 05; policy approved by Dec 10. | 2024-12-10 | Pending | 2024-12-31
RISK-004 | Operational disruption from natural disasters. | Operations | 5 | 4 | 20 | Operations Director | Disaster recovery plan, backup sites | Validate DR site and conduct simulation drill. | Drill scheduled for Nov 08; report due Nov 15. | 2024-11-15 | Planned | 2024-11-30
RISK-005 | Key personnel departure leading to knowledge loss. | Human Resources | 3 | 5 | 15 | HR Manager | Knowledge transfer documents, onboarding protocols | Implement documentation and mentorship program. | Launch program in Q4; complete by Dec 31. | 2024-12-31 | Future Action | 2025-01-31