## Worksheet
Risk Identification | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Rating | Mitigation Strategy | Ownership | Timeline | Status
Market Volatility | Fluctuations in financial markets affecting revenue projections. | 4 | 5 | High | Diversify investment portfolio and establish hedging mechanisms. | Finance Director | Q3 - Q4 | Active
Regulatory Changes | New compliance laws could increase operational costs. | 3 | 4 | Medium | Conduct regular compliance audits and engage legal advisors. | Legal & Compliance Officer | Ongoing | Planned
Supply Chain Disruption | Potential delays due to logistics or geopolitical issues. | 4 | 4 | High | Establish dual sourcing and maintain safety stock. | Operations Manager | Q4 - Next Year | In Review
Cybersecurity Breach | Unauthorized access to sensitive customer data. | 5 | 5 | Critical | Implement multi-factor authentication and advanced threat detection systems. | CISO | Immediate Action Required | Urgent