## Worksheet
Quarter | Risk Category | Risk Description | Likelihood (Low/Med/High) | Impact (Low/Med/High) | Risk Score | Mitigation Strategy | Owner | Due Date
Q1 | Operational Risk | Supply chain disruption due to supplier failure. | Medium | High | 6 | Diversify supplier base and implement backup logistics. | Logistics Manager | March 15, 2024
Q1 | Financial Risk | Currency fluctuation affecting international payments. | High | Medium | 7 | Enter into forward contracts and hedge exposures. | Finance Director | April 5, 2024
Q2 | Compliance Risk | Failure to meet regulatory updates in data privacy. | Medium | High | 6 | Conduct quarterly audits and update policies. | Legal Officer | May 20, 2024
Q2 | Technology Risk | System downtime due to outdated software. | High | Medium | 8 | Upgrade core IT infrastructure by Q3. | IT Director | June 10, 2024
Q3 | Market Risk | Decline in demand due to economic downturn. | Medium | High | 7 | Adjust pricing strategies and promote alternative products. | Sales Manager | July 25, 2024
Q3 | Reputation Risk | Negative public perception due to a product recall. | Low | High | 5 | Launch transparent communication campaign and improve product quality. | PR Director | August 15, 2024
Q4 | Human Resource Risk | Key personnel departure affecting project continuity. | High | Medium | 7 | Implement knowledge transfer programs and strengthen team structure. | HR Manager | October 5, 2024
Q4 | External Event Risk | Natural disasters affecting regional operations. | Medium | High | 6 | Develop regional contingency plans and emergency response team. | Operations Lead | November 20, 2024