## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood | Impact | Risk Rating | Mitigation Strategy | Owner | Date Identified
R-001 | Loss of critical data due to cyberattack | Cybersecurity | High | High | Critical | Implement encryption, regular audits, and employee training | IT Security Team | 2024-01-15
R-002 | Supply chain disruption due to vendor failure | Operational | Medium | High | High | Diversify suppliers and establish backup vendors | Procurement Manager | 2024-02-03
R-003 | Regulatory non-compliance leading to fines | Compliance | Low | High | High | Conduct regular compliance reviews and training | Legal Department | 2024-01-20
R-004 | Key personnel departure affecting operations | Human Resources | Medium | Medium | Moderate | Develop succession plans and cross-train staff | HR Director | 2024-03-10