## Worksheet
Task | Owner | Due Date | Risk Level | Mitigation Strategy | Status | Review Date
Conduct Risk Assessment Workshop | John Smith | 2024-04-15 | High | Engage cross-functional teams; document all potential risks. | In Progress | 2024-04-30
Identify Key Vulnerabilities in Systems | Lisa Chen | <2024-05-01 | Medium | Perform penetration testing and audit logs. | Not Started | 2024-05-15
Develop Contingency Plan for Data Loss | Mark Davis | 2024-05-10 | High | Restore from encrypted backups; implement automated alerts. | Planned | 2024-05-25
Train Employees on Risk Awareness | Sarah Lee | 2024-06-01 | Low | Monthly sessions with scenario-based drills. | Scheduled | 2024-06-15
Perform Quarterly Risk Review Meeting | Team Lead | 2024-06-15 | Medium | Evaluate updated risks and adjust controls accordingly. | Not Started | 2024-07-15