## Worksheet
Date | Task | Responsible Person | Risk Identified | Mitigation Strategy | Status | Review Date
Jan 1, 2024 | Conduct Annual Risk Assessment | John Smith | Operational Failure in Supply Chain | Implement dual sourcing for critical components | Completed | Jan 31, 2024
Feb 15, 2024 | Review Cybersecurity Vulnerabilities | Anna Lee | Data Breach Risk due to outdated software | Update firewalls and conduct penetration testing | In Progress | Mar 15, 2024
Mar 10, 2024 | Assess Regulatory Compliance Risks | David Chen | Non-compliance with GDPR | Conduct staff training and update privacy policy | Pending Review | Apr 10, 2024
Apr 20, 2024 | Develop Emergency Response Plan | Sarah Miller | Disaster Recovery Failure | Simulate disaster scenarios and update plan | Draft Submitted | May 20, 2024
Jun 1, 2024 | Perform Third-Party Risk Audit | James Taylor | Supplier financial instability | Require audited financial statements and escrow agreements | Scheduled | Jun 30, 2024
Jul 15, 2024 | Update Risk Register with New Findings | Team Lead - Risk Management | New market entry risk | Conduct SWOT analysis and scenario planning | <In Progress | Aug 15, 2024
Sep 1, 2024 | Review and Finalize Annual Risk Report | CEO Office | Executive decision-making delay due to risk exposure | Prioritize key risks in annual strategy meeting | Completed | Sep 30, 2024
Oct 10, 2024 | Conduct Risk Training for All Employees | Risk Management Team | Lack of employee awareness on risk protocols | Develop and deliver quarterly risk awareness sessions | Scheduled | Nov 10, 2024
Nov 30, 2024 | Conduct Annual Risk Review Meeting | Board of Directors | Outdated risk mitigation strategies | Review and realign risk priorities based on performance data | Completed | Dec 31, 2024
Dec 15, 2024 | Plan Next Year’s Risk Management Activities | Risk Management Office | Unclear risk landscape in emerging markets | Initiate market research and scenario planning for 2025 | Pending Review | Jan 15, 2025