## Worksheet
Date | Task | Owner | Risk Identified | Mitigation Plan | Status
2024-04-01 | Project Scope Review | Alex Morgan | Scope creep risk | Implement change control board meetings weekly | In Progress
2024-04-05 | Stakeholder Alignment Meeting | Samantha Lee | Miscommunication risk | Use standardized meeting templates and minutes distribution | Pending
2024-04-10 | Third-Party Vendor Audit | Jordan Patel | Vendor reliability risk | Require audit reports and SLA compliance checks | Planned
2024-04-15 | Data Security Assessment | Taylor Kim | Data breach risk | Conduct penetration testing and encryption review | Completed
2024-04-20 | Contingency Budget Review | Morgan Reed | Budget overrun risk | Establish clear contingency thresholds and approval process | In Progress