## Worksheet
Date | Risk Item | Owner | Risk Level | Mitigation Plan | Status | Next Review Date
2024-03-15 | Data Breach Due to Poor Access Controls | Sarah Johnson | High | Implement multi-factor authentication and role-based access. | In Progress | 2024-04-15
2024-03-18 | System Downtime During Peak Hours | Mark Thompson | Medium | Add load balancing and perform scheduled maintenance. | Pending Action | 2024-04-10
2024-03-20 | Third-party Vendor Compliance Issue | Lisa Chen | High | Conduct audit and renegotiate contract terms. | Open | 2024-04-20
2024-03-25 | Unapproved Software Installation | David Ruiz | Medium | Enforce software approval workflow and training. | Completed | 2024-05-05